## Ark1
[13 empty] | February | [31 empty] | March | [25 empty] | April
Start date: 01.02.20 |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
End date: 24.04.20 |  | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F
Planning
Project manager | Define goals | bar: SA to Week 3 W
UX-designer | Define audience | bar: SU to Week 3 W
Copywriter | Define need | bar: Week 1 M to Week 3 W
Front-end developer | Gather information | bar: Week 1 T to Week 3 F
Pre-production
Project manager | Brainstorming | bar: Week 3 SA to Week 5 F
UX-designer | Sketching | bar: Week 4 SA to Week 6 F
Copywriter | Information architecture | bar: Week 5 SA to Week 7 F
Production
Project manager | Visual plan | bar: Week 7 M to Week 7 F
Visual designer | Sitemap | bar: Week 7 SA to Week 8 F
Front-end developer | Text / pictures | bar: Week 8 SA to Week 9 F
Creating content | bar: Week 8 SA to Week 9 F
Implementation
Project manager | Prototypes / mockups | bar: Week 9 SA to Week 10 M
UX-designer | Coding | bar: Week 10 T to Week 11 M
Copywriter | Placing content | bar: Week 10 T to Week 11 M
Front-end developer
Back-end developer
Testing
Project manager | Usability testing | bar: Week 11 T to Week 11 SU
UX-designer | Manage problems | bar: Week 12 M to Week 12 TH
Copywriter | Launch | bar: Week 12 F
Front-end developer
Back-end developer